## Sheet1
Section | Tasks | Description | Owner | Status
Production Agent Set up | Prompt | Prompt with dynamic variables to pick details based on id and job id | Anshul Mishra | Done
| Basic configuration | LLM, STT, Voice | Anshul Mishra | Done
| Call settings | Configurations at agent level | Anshul Mishra | Done
| Post Call Analysis | 30 odd configs to capture details from the call | Anshul Mishra | Done
| Knowledge Base | Add benefits and dynamically pick up Job id | Anshul Mishra Hardaat Singh Baath | Done
| Tools & Workflows | Avature APIs set up | Hardaat Singh Baath | Done
| Campaign Manager Set up | Assign agent | Hardaat Singh Baath Taruna Uppala | Done
| Production Proxy | Webhook for Agent trigger to be shared with customer | Hardaat Singh Baath | Done
Concurrency | Agent Concurrency | 100 | Taruna Uppala | Done
| CM concurrency | 50 | Taruna Uppala | Done
| Telephony | Validate calls per second in Twilio (1 call per sec) | Abhishek Jain | Done
| Concurrency Setting | Agent + Voice widget to individually Support 50 conurrency | Hardaat Singh Baath | Done
Integrations | Customer Landing Page | - Avature Integration - Website to Agent set up - Input parameters - Precall workflow | Hardaat Singh Baath | Done
Testing | Avature APIs Testing | - Unit testing of all APIs - Load test of Avature APIs | Hardaat Singh Baath | Done
| Telephony Concurrency Testing | - Load test to validate CPS at Twilio - By pass Twilio CPS and test | Rakesh Ravindranath Gumaste
| Concurrency Testing | - Test 50 concurrency at the agent level - Load testing for avature api and landing page of Unifi | Rakesh Ravindranath Gumaste | Done
| Agent Testing | - Manual testing of callflow | Rakesh Ravindranath Gumaste | Done
| PCA Testing | Validate if all PCAs are capturing the right data | Rakesh Ravindranath Gumaste | Done
| Recording Upload | - Slack Notification for failure in recording update - PCA update for recording failure | Hardaat Singh Baath | Done
| Landing page for testing | Get Candidate Id and Job Id to facilitate agent testing for production | Taruna Uppala | Done
Observability | Reports Dashboard | - Latency - Call volumes - Funnel view of the calls - Disposition view - Success Criteria (Pass vs In Review) | Hardaat Singh Baath | Done
| Failure Alerts | Voice agent failures: - Workflow error - TTS error - LLM error - Telephony error - Tool Calls - External APIs error states (Avature) - Campaign manager not functional - Disposition error alerts | Hardaat Singh Baath | In progress
| Billing | View to capture volumes and MIP | Hardaat Singh Baath | Done
Infrastructure | Infra Scale Up | To suport the load of 50 concurrent calls | Hardaat Singh Baath | In progress
PCW | Additional PCA | Set up additional PCA to facilitate additional Monitoring | Gayatri Talathi
Conversation Quality | Instrumentation | High level validation of the calls quality
Notify Go-Live | Notify Go-Live | - Notify go-live on channels - Get agent added to MIP | Taruna Uppala