## Project
Task | Owner | Status | Start date | End date | Deliverable | Notes
Requirement Gathering | Taruna Uppala | In progress | 2025-09-16 | 2025-10-24
Avature Integration Endpoints | thomas.russo@unifiservice.com | In progress
Dialer Twilio |  | Not started
Dialer integration Endpoints |  | Not started
Domain landing page for agent trigger or call logic |  | Not started
List of 3 questions & Phrases |  | Completed
Mock up on Summary citations and visual citations | Abhishek Jain | In progress
List of Dispositions | Abhishek Jain | In progress
Solution Design | Taruna Uppala | In progress | 2025-09-22 | 2025-10-30
Call Script | Taruna Uppala | In progress
Call Flow Diagram | Taruna Uppala | In progress
Call Disposition Logic | Abhishek Jain | Not started
Call Retry Logic | Taruna Uppala | In progress
Avature Integration design
Development & Testing |  |  | 2025-10-27 | 2025-11-28
Agent Prompt Design
Disposition Prompt
Conversation Summarization Prompt Design
Campaign Manager Webhook for call initiation
Embedded JS file for Voice agent of Wed link
Twilio Integration
Avature Integration
Citation Development
KB Integration
File Upload/Sharing
Compliance Work
Agent Monitoring & Alerting
Milestone #1 Demo with 3 test agents |  |  | 2025-10-27 | 2025-11-07
Demo Prompt Agent
Disposition Prompt on demo data
3 Agents with different models and TTS
Demo of Monitoring Dashboard & Reporting
Final Agent Selection
Milestone #2 Demo with full integration |  |  | 2025-11-10 | 2025-11-28
Agent feedback incorporation and final agent
Integration of Avature
Integration of Telephony
Citation, KB & file upload Integration with agent
Internal Testing of Fully integated Agent
QA / UAT by Customer |  |  | 2025-11-28 | 2026-01-23
Go-Live Readiness |  |  | 2026-01-26 | 2026-01-30
production - Avature creds set up
production- Telphony set up
Setup prod Agent
Setup Reporting Dashboard
Setup Agent Monitoring

## Integrations
Title | Category | API docs URL | Type | Credentials | URL | Usecase | Status | ETA | Available in Platform | Needs Development | Comments
| Telephony |  | Sandbox |  |  |  | AWAITING |  | YES | YES
Avature | CRM |  | Sandbox |  |  |  | AWAITING |  | NO | YES
| Appointment |  | Sandbox |  |  |  | AWAITING |  | NO | YES
HRMS
ITSM

## Agent Feedback
Owner | Date & Time of Call | Record what you said to the agent | How did the agent respond | How should the agent have responded | Other Notes/Observations
Jennifer (6617) |  | I don't remember applying | She said she showed I applied to the position and asked if I want to proceed.
Jennifer (6617) |  | I don't remember applying (2) | She said I see you applied to the ramp agent position.. And then said perfect with no pause in between and moved on. (not sure if she thought I said something- I didn't)
Jennifer (6617) |  | I don't remember applying (3) | She said sorry about the mix up, we may have gotten the job title mixed up and went to end the call. There was a long pause and I ultimately said wait I will interview anyway and she agreed to proceed with the call.
Jennifer (6617) |  | I don't remember applying (4) | She said thank you Rodger if you don't remember the specific position you applied for that is okay we can still move forward with the screening.
Jennifer (6617) |  | I don't remember applying (5) | She said thank you for confirming Rodger I will continue with the interview for the ramp agent position
Jennifer (6617) |  | Unprompted on my end | On one call when asking if I was Rodger and did I apply to the ramp agent position, I said yes and the agent paused for a long time, eventually I asked did you hear me and the agent said yes I am waiting on you to confirm your name and position you applied to | Should not happen and if the agent didn't hear me they should reask the question itself not leave it now open ended with the candidate
Jennifer (6617) |  | Can I do this screening at a different time | She asked when would be a better time and said she would have our team call then | The agent will not be scheduling calls back, the candidate can refer to the text or email they received to retrigger the call at a later time.
Jennifer (6617) |  | I cursed when being asked the first question | She said I understand this is a suprising question and prompted me to answer the question again | When a candidate uses innaproriate language like cursing or belittling/abusive language the agent should respond similar to a human- where you would stop the call and say I recognize you are frustrated with this screening call but the language being used isn’t appropriate for this conversation. For that reason, I’ll need to end the call here.
Jennifer (6617) |  | I cursed at the agent a few times and expressed frustration and annoyance with the agent multiple times being rude | The agent apologized and throughout allowed me to continue the call if I wanted | When a candidate uses innaproriate language like cursing or belittling/abusive language the agent should respond similar to a human- where you would stop the call and say I recognize you are frustrated with this screening call but the language being used isn’t appropriate for this conversation. For that reason, I’ll need to end the call here.
Jennifer (6617) |  | I paused and said Hmm after being asked the first question | She said thank you (registering an answer) and moved on to the next question quickly | Should not register Hmm's or similar responses like okay, uhh or mm's as responses to the question but rather a candidate taking a moment to think.
Jennifer (6617) |  | How long will it take to hear back? | She said our team usually reviews applications within a month | A month is too far out - we should say specific time lines may vary based on hiring need and volume of applications and not give a set time frame.
Jennifer (6617) |  | No prompt on my end, answering last question | Agent cut me off mid sentence and was ready to end the call, when she asked if I had any questions at the end of the call I said yes you cut me off and I wasn't done answering the last question, she apologized and told me I could finish answering the question. Completed the call fine from there. | Agent cut me off on a few of my testing calls, we should improve, I conducted these calls in a quiet space and was speaking clearly at a normal cadence.
No | Testing Action | Agent Response | Notes
1 | I don't remember applying | She said she showed I applied to the position and asked if I want to proceed. | Agent response to the candidate saying they don't remember applying to the ramp agent position is inconsistent. I like the response where the agent said they showed that I had applied and asked if I wanted to proceed.
2 | I don't remember applying (2) | She said I see you applied to the ramp agent position.. And then said perfect with no pause in between and moved on. (not sure if she thought I said something- I didn't)
3 | I don't remember applying (3) | She said sorry about the mix up, we may have gotten the job title mixed up and went to end the call. There was a long pause and I ultimately said wait I will interview anyway and she agreed to proceed with the call.
4 | I don't remember applying (4) | She said thank you Rodger if you don't remember the specific position you applied for that is okay we can still move forward with the screening.
5 | I don't remember applying (5) | She said thank you for confirming Rodger I will continue with the interview for the ramp agent position
6 | My name is not Rodger but can I interview anyway | The agent appreciated my interest but that we could not continue the call. | Good Response
7 | I don't want the call recorded | She said she understood but gave explanation as to why it was needed and it is a requirement to move forward | Good Response
8 | Unprompted on my end | On one call when asking if I was Rodger and did I apply to the ramp agent position, I said yes and the agent paused for a long time, eventually I asked did you hear me and the agent said yes I am waiting on you to confirm your name and position you applied to | Should not happen and if the agent didn't hear me they should reask the question itself not leave it now open ended with the candidate
9 | Can I do this screening at a different time | She asked when would be a better time and said she would have our team call then | The agent will not be scheduling calls back, the candidate can refer to the text or email they received to retrigger the call at a later time.
10 | Are you a real person? | She said she is a Virtual AI Recruiter | Good Response
11 | Can I talk to a human instead | She is unable to transfer to a human and said it is okay if I want to decline this screening | Good Response
12 | I cursed when being asked the first question | She said I understand this is a surprising question and prompted me to answer the question again | When a candidate uses inappropriate language like cursing or belittling/abusive language the agent should respond similar to a human- where you would stop the call and say I recognize you are frustrated with this screening call but the language being used isn’t appropriate for this conversation. For that reason, I’ll need to end the call here. You can reach back out to your recruiter if you’d like to proceed later.
13 | I cursed at the agent a few times and expressed frustration and annoyance with the agent multiple times being rude | The agent apologized and throughout allowed me to continue the call if I wanted
14 | Can you see the other positions I applied to? | No I can only see this application | Good Response
15 | I paused and said Hmm after being asked the first question | She said thank you (registering an answer) and moved on to the next question quickly | Should not register Hmm's or similar responses like okay, uhh or mm's as responses to the question but rather a candidate taking a moment to think.
16 | I said I never want to be contacted again (didn't verify my identity) | Said she would update our records right away so we don't get any further calls | How will that happen? Will it real time trigger something to stop our auto-reminders? If opting the candidate out is going to require a human recruiter review to disposition then we should re-word the agents response that you will let the recruiting team know so they can update you application.
17 | How long will it take to hear back? | She said our team usually reviews applications within a month | A month is too far out - we should say specific time lines may vary based on hiring need and volume of applications and not give a set time frame.
18 | No prompt on my end | Agent asked for my applicant ID number at the end of the call. | We should ask this at the beginning of the call when we are verifying the candidate.
19 | No prompt on my end, answering last question | Agent cut me off mid sentence and was ready to end the call, when she asked if I had any questions at the end of the call I said yes you cut me off and I wasn't done answering the last question, she apologized and told me I could finish answering the question. Completed the call fine from there. | Agent cut me off on a few of my testing calls, we should improve, I conducted these calls in a quiet space and was speaking clearly at a normal cadence.

## Additional Feedback
Call Type | Date | Time | Nurix Disposition | Notes
Very positive answers but not relevant to the question or not specfic at all. | 2025-11-19 | 1:37 PM ET | Review | Okay
Started each answer with a sarcastic or negative response to the question itself but went on to answer the question positively. | 2025-11-19 | 1:41 PM ET | Passed | Candidate should not have been passed
Short answers | 2025-11-19 | 1:45 PM ET | Review | The AI tool should prompt candidates who give very short answers to elaborate or share more.
Attempt at giving negative answers that use a lot of positive buzz words (issues with call) | 2025-11-19 | 3:40 PM ET |  | I was cut off by the agent so wasn't able to finish the call as intended.
Used a lot of double negatives | 2025-11-20 | 3:40 PM ET | Review | Answers were positive, should have passed
Started the answers off negatively but also used a lot of positive keywords (ex: Well if I like that coworker I would….) | 2025-11-20 | 4:25 PM ET | Passed | Should not have been passed.
Gave sarcastic answers | 2025-11-20 | 4:30 PM ET | Passed | Should have been a review
Gave positive answers but used a lot of negative words | 2025-11-20 | 4:36 PM ET | Passed | Okay
Gave answers with good intent but tried to add a lot of fluff not concise answers | 2025-11-20 | 4:47 PM ET | Passed
Short but good answers | 2025-11-20 | 4:51 PM ET | Passed | Okay
Not negative answers but not clearly positive. | 2025-11-20 | 4:56 PM ET | Passed | Answers were vague and a good example of a review case.
Started the answers off negatively (ex: if it's a good day I would etc.) but then ended in a good answer. | 2025-11-21 | 5:19 PM ET | Passed | Should not have been passed.

## Other Sources
Title | Doc Link | Status | Comments | ETA
Solution Doc |  | YET TO ASK
Call Recordings (pre-recorded sales calls) |  | YET TO ASK
Call Scripts | Nurix script Revision.docx | YET TO ASK
Knowledge Base | Knowledge Base | YET TO ASK
Success Metrics |  | YET TO ASK
Guardrails |  | YET TO ASK
Monitoring Dashboard |  | YET TO ASK
Call Preprocessing Flow |  | YET TO ASK
Call Flow Diagram | https://www.figma.com/board/uhQe0Z5noNLDVywcXmWlrl/Unifi?node-id=83-788&t=VNHNCI4kbFbXexf5-0 | YET TO ASK
Call postprocessing Flow |  | YET TO ASK
Reporting Requirement |  | YET TO ASK
3 questions & answers | Nurix Call Requirements and Questions 2.docx

## Use Case (hidden)
Sl No | Use Case | Description | Business Process |  | Success Criteria | Business Impact |  |  | Overall Revenue Impact Aimed | Karthik Viswanathan / Prashant Kumar Tiwari, can you please help me fill this sheet
|  |  | Current | Proposed |  | Evaluation Metric | Current | Target
1 | Lead Validation | As soon as customer books a demo, a call is triggered to explain the program and validate all details. Aim is to ensure right info is captured prior to demo, reduce inefficiency, and remind for demo. | High demo drop-offs due to invalid data/lack of clarity. | Voice AI validates leads, explains demo, and sends reminders. Ops effort reduced, lead quality improved. | - Leads validated promptly - Invalid/incomplete leads flagged to CRM - Higher demo attendance among verified leads | Demo Attendance @ 57% | Higher attendance, less manual validation
2 | Demo Rebooking | For customers who miss their demo, follow-up calls are triggered at intervals (24h, 7d, 30d) to rebook, using WhatsApp links for easy rescheduling. | Ops team spends time on manual follow-up for drop-outs. | Automated AI calls & WhatsApp for self-service rebooking; less manual chasing by ops. | - Increase in rebooked demos - Recovery % of missed demos - Ops time spent on follow-ups reduced | Low rebooking, high manual effort | Higher recovery, reduced ops workload
3 | Inbound Call-back Request | Any inbound call request by a parent is handled by an AI agent for L0 queries; L1/L2 queries are escalated to Sales or tickets are created. | Sales handles all inbound queries manually. | AI handles basic queries, escalates only complex ones. | - % of L0 queries resolved by AI - Avg. sales handling time per ticket - Parent satisfaction with support | Sales handles all, slow response times | Faster responses, more sales bandwidth
4 | Onboarding Calls | On first class date, trigger a call to onboard new customers: share next steps, support details, and ensure smooth start. | Unstructured onboarding, leading to confusion. | Proactive onboarding call by AI, guidance given, queries answered. | - % of customers onboarded via call - Reduction in onboarding-related queries - Positive onboarding feedback | Support tickets/queries from new customers | Smoother onboarding, fewer support tickets
5 | Pulse Calls | After 4 classes, call customer to check experience and ask if help is needed. | No structured feedback collection after classes begin. | Automated “pulse” calls for early feedback and issue resolution. | - % of customers giving feedback - # of issues identified early - Improvement in satisfaction/retention scores | Delayed feedback, reactive issue handling | Improved retention, proactive support
6 | Reminder Calls to Choose Slots | Trigger automated reminder calls for booking paid class slots. | Manual reminders or no reminders; missed bookings. | AI calls customers at optimal time to prompt booking. | - % increase in slot bookings - Reduction in manual reminders sent - Slot booking completion rate | Manual chasing, low slot booking rates | Higher bookings, less manual work
Lead Validation ,Demo Rebooking ,Inbound Call-back Request ,Onboarding Calls ,Pulse Calls ,Reminder Calls to Choose Slots
Note:
# Business Process, Success Criteria, Business Impact information to be reviewed and validated by Sales Team
Revenue/Cost Impact to be detailed post project completion if required information is available

## Questionnaire Tab
L1 Category | L2 Category | Question | Unifi Answer
Use Case Deepdive | Define the Use Case: | What is the primary use case for this project? (e.g., Lead Qualification)
Please provide a brief description of the current user funnel journey for this use case.
| Current Process: | How is this use case currently handled without Nurix?
What tools, processes, or teams are involved in managing this today?
What is the expected daily call volume for this project.
How many human agents are currently available, and in which situations might a human handover be required?
| Future Process with Nurix: | How do you envision solving this use case with Nurix?
Please share a brief overview of the ideal solution
| Scope Specifics: | What regions, languages, and accents are relevant for this requirement?
| Human Interaction: | Is immediate transfer to a human agent required for escalations, qualified leads, or other scenarios?
If yes, please provide details regarding APIs and logic to ensure minimal wait time for customers.
| Software Coordination: | Apart from CRM and dialers, what other systems should the voice AI agent integrate with?
Data Requirements | Call Recordings: | Could you please share high-quality, real call recordings to help us understand the best practices being followed today?
| Call Flow Structure: | Please provide a detailed structure of the current call flow/scripts, highlighting any key nuances or edge cases.
| Reference Materials: | Please share any FAQs, handbooks, or policy documents that agents currently use to handle conversations. (e.g., policy details, guidelines, etc)
| Post-Call Analytics: | What key insights should be captured post-call? (e.g., call dispositions, summaries, notes, sub-statuses)
| Follow-Up Logic: | Do you want the Voice AI agent to schedule and execute follow-ups? If yes, please outline the call scheduling logic in different cases such as call-back, escalation, etc.
| CRM Field Mapping: | We will need the exact mapping of call dispositions to CRM fields to ensure smooth data integration.
| Data flowing to Nurix | What user information the Voice AI agents will have while initiating the call, how do we plan to use that information to make the conversation more personalized and engaging?
Integrations | CRM Integration: | What CRM system is currently in use?
Please share the available APIs to facilitate integration?
Is there flexibility in defining the payload that will be passed while triggering the Nurix endpoint? (e.g., previous call context, current lead status, lead name, etc.)
| Dialer System: | What dialer system is currently used? Does it support SIP trunking for Voice AI integration?
Nurix has native integrations with Twillio and Plivo, are we open to using them? The commercials would be billed at actuals.

## Call Flow
Outbound Flow
Question | Customer's Comments | Nurix's Comments
Scenario A: Call Not Picked Up
How many call attempts should be made before categorizing the customer as “No Response”? |  | Industry Standard : 3-5 attempts
What is the interval between follow-up call attempts? |  | Industry Standard 2nd Attempt: 2-4 hours later or next business day. 3rd Attempt: Within 24-48 hours of the second attempt. 4th Attempts : 2 days after the 2nd attempt. 5th Attempts: 3 days after the 4th attempt.
What should be the allowed calling window for different geographies?
Scenario B: Call Picked Up and Connected
What action to take when the lead is succesfully qualified ? |  | -Do we need to update certain fields in CRM if yes , please specify the fields and the logic -Do we need to create a ticket if yes , please help with the structure.
When a user requests to update child name, age, course details, or WhatsApp number, which CRM fields should be updated?
How to categorize the different types of leads and the logic behind this. |  | - Hot / Dormant .etc
If there is another flow please assist with the details.
Scenario C : Call Dropped Mid-Conversation
Within what timeframe should we attempt an immediate callback after disconnection ? |  | Ideal Callback Timeframe: Within 2 minutes after call drop.
What details should we record if the call fails to reconnect immediately ?
If the call doesn’t connect immediately, should we follow the same callback retry logic as the initial call, or implement a different workflow ?
Scenario D: Customer Requests Callback Later
What specific information should we capture when scheduling a customer-requested callback?
When a user requests a specific reschedule time, should we create a ticket, send WhatsApp, or update CRM directly?
What process should we follow if the scheduled callback does not connect? Should it mirror the “Call Not Picked Up” logic, or follow an alternate approach?
Which CRM columns should be updated for a reschedule, and do we need to do any action (For e.g send a whatsapp msg/ create a ticke)
Scenario E : Call Attempt Fails Immediately (Technical Issues, Number Invalid)
After how many unsuccessful validation attempts should the issue be escalated for manual review?
Scenario F : Ticket Creation
Please assist with the details on the format to create the tickets |  | For e.g : Suject : Nurix - Reschedule .etc
Please assist the primary information you want us to pass. |  | For e.g : Call Summary , Mark Ticket with as Urgent .etc
Logic's on how to pass this formation |  | Based upon querys how to categorise the tickets
Scenario G : Reporting & Dispositon Mappings
Is there need for any customer reports / except for the out of the box reports |  | If yes, please provide deatils around it.
What is the expected daily call volume for this project.
What key insights should be captured post-call? (e.g., call dispositions, summaries, notes, sub-statuses)
When a user is not interested in the demo or reschedule, should we create a ticket or only update CRM fields? If we need to update the CRM , which CRM fields.
What should be the behaviour if the user requests information beyond agent’s access (e.g., fee breakdown, specific tutor profile)?